## Roadmap
Phase | Duration | Focus | Primary output | Exit gate
0 | 2 weeks | Discovery & pilot | Partner commitments and KPIs | 2 design partners + MVP metrics
1 | 6 weeks | Regulatory research | Versioned standards registry | Sources, applicability trees, expert review
2 | 4 weeks | Information architecture & UX | Tested prototype | 2 consultants complete a flow
3 | 8 weeks | Multi-tenant core | Secure workspace | Isolation, roles, projects work
4 | 8 weeks | TR reporting MVP | Activity + TSRS/GRI + DOCX | One real/anonymised report delivered
5 | 6 weeks | Grounded Claude assistant | Source-linked AI | No uncited AI output
6 | 8 weeks | CBAM MVP | One-sector evidence consistency | 90% critical test cases caught
7 | 5 weeks | Interactive KPI studio | Embeddable data stories | KPI source visible < 2 clicks
8 | 8 weeks | Pilot & productization | 2 tenants / 3 client workspaces | Retention and security evidence
9 | Months 10–12+ | EU extension | First country pack | Expert-reviewed local/EU package

## Sources
Jurisdiction | Area | Source / Standard | Status to validate | Product pack | Why it matters | Official URL
TR | Annual / Activity Report | Yıllık Faaliyet Raporunun Asgari İçeriği Yönetmeliği | In force; validate consolidated text | TR Activity Report Core | Minimum content and report structure | https://www.mevzuat.gov.tr/anasayfa/MevzuatFihristDetayIframe?MevzuatTur=7&MevzuatNo=16547&MevzuatTertip=5
TR | Annual / Listed companies | SPK II-14.1 | In force; verify current amendments | TR Listed Company Add-on | Annual and interim board activity report requirements | https://spk.gov.tr/data/61e367981b41c6127032080b/0b0e02a3-6a94-4573-a771-2e7b73a3e639.pdf
TR | Sustainability | TSRS 1 | In force; monitor amendments | TSRS Core | General sustainability-related financial disclosures | https://www.kgk.gov.tr/Portalv2Uploads/files/Duyurular/v2/Surdurulebilirlik/RaporlamaStandarti/TSRS%201.pdf
TR | Sustainability | TSRS 2 | In force; monitor amendments | TSRS Climate | Climate disclosures and metrics | https://kgk.gov.tr/Portalv2Uploads/files/Duyurular/v2/Surdurulebilirlik/Duyuru/(KaynaklarIslenmis)_TSRS%202.pdf
TR | Sustainability scope | KGK TSRS scope decision | In force; verify scope/transition | Applicability Engine | Mandatory scope, thresholds and transition | https://www.kgk.gov.tr/Portalv2Uploads/files/Duyurular/v2/Kurul%20Kararlar%C4%B1/TMS%20Kurul%20Kararlar%C4%B1/T%C3%BCrkiye%20S%C3%BCrd%C3%BCr%C3%BClebilirlik%20Raporlama%20Standartlar%C4%B1n%C4%B1n%20Uygulama%20Kapsam%C4%B1na%20ili%C5%9Fkin%20Kurul%20Karar%C4%B1.pdf
EU | Annual report | Accounting Directive 2013/34/EU | In force; local transposition needed | EU Management Report Core | Annual accounts and management report framework | https://finance.ec.europa.eu/financial-markets/company-reporting-and-auditing/company-reporting/financial-reporting_en
EU | Listed annual report | ESEF / Transparency requirements | In force; issuer profile needed | EU Listed Add-on | XHTML/iXBRL annual report conditions | https://finance.ec.europa.eu/financial-markets/company-reporting-and-auditing/company-reporting/transparency-requirements-listed-companies_en
EU | Sustainability | CSRD / ESRS | Current acts and local implementation must be validated | EU ESRS Core | Sustainability statement and ESRS framework | https://finance.ec.europa.eu/financial-markets/company-reporting-and-auditing/company-reporting/corporate-sustainability-reporting_en
EU | Sustainability timing | Directive 2025/794 | In force | EU Applicability Engine | Postpones certain reporting dates | https://eur-lex.europa.eu/legal-content/EN/TXT/HTML/?uri=OJ%3AL_202500794
EU | Sustainability scope | Directive 2026/470 | In force; profile and member-state law required | EU Applicability Engine | Omnibus I scope/process amendments | https://eur-lex.europa.eu/legal-content/EN/TXT/HTML/?uri=OJ%3AL_202600470
EU | Sustainability / voluntary | Regulation 2026/1560 | In force; validate exact tenant relevance | VSME / Value chain | Voluntary sustainability standard research point | https://eur-lex.europa.eu/legal-content/EN/TXT/?uri=OJ%3AL_202601560
EU | Sustainability | Regulation 2026/1563 | In force; validate report-period applicability | ESRS rules | Revised ESRS / transitional provisions research point | https://eur-lex.europa.eu/legal-content/EN/TXT/?uri=OJ%3AL_202601563
EU | Taxonomy | EU Taxonomy | Active revision monitoring | Taxonomy Module | Environmental activity and disclosure research | https://finance.ec.europa.eu/sustainable-finance/platform-sustainable-finance_en
EU | CBAM | CBAM definitive period guidance | Current official guidance | CBAM Evidence Module | Annual declaration, evidence, roles and calculation boundaries | https://taxation-customs.ec.europa.eu/system/files/2026-08/Guidance%20No.%201%20-%20Introduction%20to%20CBAM%20concepts.pdf
EU | CBAM | CBAM verification | Current official guidance | CBAM Evidence Module | Actual emissions verification and accreditation | https://taxation-customs.ec.europa.eu/carbon-border-adjustment-mechanism/cbam-verification_en
Global | Sustainability | GRI 1 / 2 / 3 | In force; add relevant current Topic/Sector standards | GRI Core | Foundation, general disclosures, material topics | https://globalreporting.org/pdf.ashx?id=12334

## MVP Backlog
ID | Epic | Feature | Priority | Phase | Acceptance criterion
MZ-001 | Multi-tenant | Tenant, client organisation and reporting-cycle model | Must | 3 | Two tenants cannot access each other's data in integration test
MZ-002 | Security | Roles, audit log and document permissions | Must | 3 | Every material change is traceable to actor/time/version
MZ-003 | Profile | Corporate Master Profile | Must | 3 | Company profile data can be reused in two report projects without duplicate entry
MZ-004 | Blueprint | Report type and index composer | Must | 3-4 | System creates mandatory/conditional/editorial section plan
MZ-005 | Standards | TR activity report, TSRS and GRI starter packs | Must | 4 | Every generated requirement shows source/version/owner
MZ-006 | Workflow | Data request, ownership, deadline and approval | Must | 4 | A section cannot become Word-ready without required approvals
MZ-007 | Data | Excel import, evidence attachment and metadata | Must | 4 | Each metric records period, unit, scope and source
MZ-008 | Rules | Units, totals, period, source and version checks | Must | 4 | Critical malformed test records are flagged
MZ-009 | Output | Word Report Compiler v1 | Must | 4 | DOCX contains approved content, tables, source IDs and pending items
MZ-010 | AI | Claude grounded evidence assistant | Must | 5 | Every answer contains sources or a clear insufficiency flag
MZ-011 | CBAM | Product-site-energy-emissions evidence model | Must | 6 | A report trace can be navigated product→evidence
MZ-012 | CBAM | Consistency rules for one pilot sector | Must | 6 | ≥90% of designed critical inconsistency cases caught
MZ-013 | Visual | Interactive KPI Studio | Should | 7 | Every KPI exposes scope, period, definition and source
MZ-014 | Visual | Report Relationship Map | Should | 7 | User can see reused/conflicting data across report tracks
MZ-015 | Commercial | White-label tenant settings | Should | 8 | Tenant can configure logo, colour, workspace domain label
MZ-016 | EU | EU ESRS / management report starter pack | Could | 9 | Pilot country profile passes expert review

## Research Decisions
Decision | Why it matters | Owner | Status
Pilot sector for CBAM | Defines data model and formula/test scope | Product lead + CBAM expert | Open
First report package | Prevents trying to support all standards at once | Product lead + reporting expert | Open
First EU member state | Annual-report legal details vary by member state | EU legal expert | Open
Standard update SLA | Keeps rule packs current | Regulatory lead | Open
LLM data policy | Sets permitted models and sensitive-data boundaries | Security lead | Open
Word template system | Defines agency handoff and style mapping | Agency lead | Open